## Web Admin>Client_Management
Environment
Tester's Name : Noor Afida Annha |  |  | Reviewed By
Date Tested |  |  | Version
Issue Id | Module | Issue Title | Description | Steps to Reproduce | Issue Type | Priority | Severity | Actual Result | Expected Result | Attachment | Status | Comments
1 | Update Profile(Choose File Field) | Profile picture file name overflows field and allows unsupported file types | In the "Update Profile" section of the admin panel under "Manage Client," the following issues were observed: 1.After choosing a file in the "Choose File" section for the profile picture, the file name overflows outside the designated input field instead of being truncated or displayed properly within the field. 2.The file upload functionality allows unsupported file types, such as PDF and music files, which should be restricted to image formats (e.g., JPEG, PNG). | 1.Log in to the website. 2.Navigate to Admin Panel > Manage Client > Client Profile > Update Profile. 3.In the "Choose File" section: ->Select a file with a long file name and observe how it overflows the input field. ->Select unsupported file types (e.g., PDF or MP3) and observe that the system allows these files to be chosen. | Bug | High | Medium | 1.The file name overflows outside the designated input field, causing a UI issue. 2.Unsupported file types, such as PDF and MP3, can be selected without any restriction or validation error. | 1.The file name should be displayed properly within the field, either truncated with ellipsis (...) or wrapped neatly without overflowing. 2.The system should only allow image file types (e.g., JPEG, PNG, GIF) to be selected and should display an error message for unsupported file types. | https://postimg.cc/gallery/DnhKyX9 | Ready for QA
2 | Update Profile(Email Field) | Email input field allows invalid or non-existent email addresses to be updated without verification | In the email input field of the profile update section, users can input and save invalid or non-existent email addresses without any validation or verification. The system does not validate the email format, check the email's existence, or require verification, allowing updates with incorrect or fake email addresses. | 1.Navigate to the email input field in the "Update Profile" section. 2.Input an invalid email format (e.g., example@.com, abc@xyz ). 3.Save the changes. 4.Observe that the system accepts and updates the invalid email address without showing an error or requesting email verification. | Bug | High | High | Invalid email formats and non-existent email addresses are accepted and updated in the user profile without any validation or verification. | 1.The system should validate the email format before accepting the input. 2.Invalid email addresses should trigger an error message, such as: "Invalid email address. Please enter a valid email." 3.The system should also verify the email's existence (e.g., via an OTP or verification email) before updating it in the profile. |  | Ready for QA
3 | Update Profile(Phone Number Field) | Country code dropdown displays inconsistent red and black dots next to certain country codes | In the phone number input field where users can select a country code, some country codes are preceded by a red dot, while others show a black dot. The presence of these dots is inconsistent and lacks any explanation or purpose, leading to confusion for the user. | 1.Navigate to the phone number input field in the relevant section (e.g., registration or profile update page). 2.Open the country code dropdown list. 3.Observe the dots displayed next to certain country codes. ->Some codes have a red dot. ->thers have a black dot. 4.Note that there is no pattern, explanation, or consistency for these dots. | Bug | Low | Low | Red and black dots are inconsistently displayed next to certain country codes in the dropdown, with no explanation for their purpose. | 1.The country code dropdown should display a clean and consistent design without any unexplained red or black dots. 2.If dots are intended for a specific purpose, their meaning should be clearly conveyed (e.g., a tooltip or legend). | https://postimg.cc/gallery/wJjHT0H | To do
4 | Update Profile(Phone Number Field) | Inconsistent display of country flags in the country code dropdown | In the phone number input field, where users can select a country code, some country codes are accompanied by their respective country flags, while others do not display any flags. This inconsistency leads to a poor user experience and may confuse users about the purpose or functionality of the dropdown. | 1.Navigate to the phone number input field in the relevant section (e.g., registration or profile update page). 2.Open the country code dropdown list. 3.Observe that some country codes are displayed with their respective country flags, while others do not show any flags. | Bug | Medium | Low | Some country codes display their respective country flags, while others do not have any flags, causing inconsistency in the dropdown UI. | The country code dropdown should consistently display flags for all countries or not display flags at all. If flags are displayed, they should match the respective country codes. | https://i.postimg.cc/qRS6syZg/phn-p-show.jpg | To do
5 | Update Profile(Phone Number Field) | Duplicate country flags displayed consecutively in the country code dropdown | In the phone number input field where users can select a country code, some countries are displayed with the same flag appearing consecutively in two rows. This duplication causes confusion and affects the dropdown's usability and visual consistency. | 1.Navigate to the phone number input field in the relevant section (e.g., registration or profile update page). 2.Open the country code dropdown list. 3.Scroll through the dropdown and observe that some countries are displayed with the same flag in two consecutive rows. | Bug | Medium | Low | Some countries are displayed with the same flag in consecutive rows, leading to unnecessary duplication in the dropdown list. | 1.Each country should appear only once in the dropdown list with its respective flag and country code. 2.There should be no duplicate rows for any country. | https://i.postimg.cc/L6dZhk1b/phn-same.jpg | To do
6 | Update Profile(Phone Number Field) | Missing or incorrect country flag in the country code dropdown | In the phone number input field where users can select a country code, some countries in the dropdown list show no flag at all. This inconsistency impacts the accuracy and usability of the dropdown. | 1.Navigate to the phone number input field in the relevant section (e.g., registration or profile update page). 2.Open the country code dropdown list. 3.Scroll through the list and observe that: ->Some countries do not display their respective flags. | Bug | Medium | Medium | Some countries in the dropdown list are missing their flags. | Each country in the dropdown should display its correct and respective flag next to its country code. | https://postimg.cc/gallery/tC8N9My | To do
7 | Update Profile(Phone Number Field) | Phone number input allows invalid digit lengths not aligned with country-specific rules | In the phone number input field, users can save a phone number with only one digit or more digits than allowed for a specific country's format. For example: ->Bangladesh numbers should allow only 11 digits but can currently accept more or fewer digits. ->Users can also save phone numbers with a single digit, which is invalid as no country supports such phone numbers. The system does not validate phone numbers against country-specific digit rules, allowing invalid inputs. | 1.Navigate to the phone number input field in the relevant section (e.g., registration or profile update page). 2.Select any country code (e.g., Bangladesh). 3.Input a phone number with: ->Fewer digits than required (e.g., one digit). ->More digits than required (e.g., 15 digits for Bangladesh). 4.Save the phone number. 5.Observe that the system accepts the invalid phone number without validation. | Bug | High | High | The system allows users to save phone numbers with one digit or an invalid number of digits for the selected country. | 1.The system should enforce country-specific rules for phone number lengths. 2.Users should only be able to input phone numbers matching the digit format for the selected country code. 3.Single-digit phone numbers should be rejected for all countries. | https://postimg.cc/gallery/t9Jpnmb | Ready for QA
8 | Update Profile(Profile Picture) | Uploaded profile photo becomes blurry after upload | When a user uploads a photo for their profile in the update section, the uploaded photo appears blurry. This affects the display quality of the profile photo, even if the original uploaded image is of high resolution. | 1.Navigate to the Update Profile section in the Manage Client page. 2.Click on the Choose File button and upload a high-resolution photo. 3.Save the changes to upload the photo. 4.Observe the profile photo after the upload is complete. | Bug | Medium | Medium | The uploaded profile photo appears blurry and does not retain the quality of the original image. | The uploaded profile photo should retain its original quality and resolution after being uploaded and displayed in the user’s profile. | https://i.postimg.cc/jSbg6JG8/profile-photo.jpg | To do | It's not an issue
9 | Update Profile(Address Field) | Invalid characters allowed in the address field (e.g., "---------------") | In the update profile section, the address field allows users to input invalid characters like "---------------" (or other arbitrary characters), which is not a valid or meaningful address format. The system should restrict or validate the input to ensure only valid address data is accepted. | Navigate to the Update Profile section. In the Address field, input invalid characters like "---------------". Save the changes. Observe that the invalid input is accepted and saved without validation. | Bug | Medium | Medium | The system allows invalid input like "---------------" in the address field and saves it without any validation or error message. | The address field should validate the input to ensure that only valid address formats are accepted. Invalid characters, such as a series of dashes or other nonsensical strings, should trigger a validation error and not be allowed. | https://i.postimg.cc/BvvCN5NC/address.jpg | To do | It's not an issue
10 | WhatsApp->Segments | Table border disappears when scrolling horizontally in the segments section | In the Segments section under Admin Panel -> Client Management -> WhatsApp -> Segments, the table displaying the list of segments has an issue with its borders. When the user scrolls the table horizontally, the borders on either the left or right side of the table disappear, depending on the direction of the scroll. This creates an incomplete visual display of the table. | 1.Navigate to the Admin Panel and go to Client Management -> WhatsApp -> Segments. 2.Scroll horizontally using the scrollbar on the segment list table. 3.Observe that when scrolling to the left, the right side of the table's border disappears. 4.When scrolling to the right, the left side of the table's border disappears. | Bug | Medium | Low | The left and right borders of the table disappear when the user scrolls in the respective direction (left or right). | The borders of the table should remain visible on both the left and right sides, even when scrolling horizontally. The table should have a consistent border around all sides, regardless of scrolling direction. | https://postimg.cc/gallery/hz1tDvK | To do
11 | WhatsApp->Segments | Search icon in the segments section is unresponsive | In the Segments section under Admin Panel -> Client Management -> WhatsApp -> Segments, the search icon in the search bar is unresponsive. When the user enters a keyword into the search field and clicks the search icon, nothing happens, and no results are displayed. This prevents users from searching for specific segments efficiently. | Navigate to the Admin Panel and go to Client Management -> WhatsApp -> Segments. Locate the search bar at the top of the segment list table. Enter a keyword into the search field (e.g., a segment name). Click on the search icon (magnifying glass). Observe that nothing happens and no search results are shown. | Bug | High | Medium | Clicking the search icon does not trigger any action, and no results are shown after entering a keyword in the search bar. | When a user enters a keyword in the search bar and clicks the search icon, the system should return matching results from the segment list. The search functionality should be responsive and show relevant segments based on the input keyword. | https://postimg.cc/gallery/NrY7zpQ | Ready for QA
12 | WhatsApp->Segments | Table format displayed incorrectly on the second page of the segments list | In the Segments section under Admin Panel -> Client Management -> WhatsApp -> Segments, when navigating to the second page of the segment list table, the table format is displayed incorrectly. Some cells in the table have spaces where borders should be, leading to a misalignment of data and a broken layout. This issue affects the presentation and makes the table look unorganized. | 1.Navigate to the Admin Panel and go to Client Management -> WhatsApp -> Segments. 2.View the segment list on the first page. 3.Navigate to the second page of the segment list using the pagination controls. 4.Observe the table format on the second page. 5.Notice the spaces where borders should be present, causing misalignment in the table’s layout. | Bug | Medium | Medium | The table on the second page of the segment list displays incorrectly, with some cells missing borders, causing a disorganized layout and misaligned data. | The table on the second page should maintain the correct formatting, with consistent borders around each cell, ensuring the data is properly aligned and presented. The appearance should be uniform across all pages of the segment list. | https://i.postimg.cc/43wkKTxx/segment-2nd-page-box.jpg | To do
13 | WhatsApp->Segments | Excessive horizontal scrollbar in the segments table | In the Segments section under Admin Panel -> Client Management -> WhatsApp -> Segments, the horizontal scrollbar is unnecessarily long and spans the entire length of the table. This results in poor usability as the scrollbar is redundant; all data is already visible without requiring horizontal scrolling. The scrollbar's presence creates unnecessary clutter in the UI. | Navigate to the Admin Panel and go to Client Management -> WhatsApp -> Segments. View the table displaying the list of segments. Observe the horizontal scrollbar at the bottom of the table, which is as long as the table's width. Note that all data is already visible without needing horizontal scrolling. | Bug | Medium | Low | The horizontal scrollbar appears unnecessarily and spans the entire width of the table, even though it is not needed as all data is visible without scrolling. | The horizontal scrollbar should either not appear at all or be appropriately sized based on the table's content. Ideally, the table should be designed to display all data within the viewport, eliminating the need for a horizontal scrollbar entirely. | https://i.postimg.cc/pVKN88TS/segment-can-t-scroll.jpg | To do
14 | WhatsApp->Segments | Vertical scrollbar misaligned with the table in the segments section | In the Segments section under Admin Panel -> Client Management -> WhatsApp -> Segments, the vertical scrollbar appears on the far right side of the page, aligned with the entire page instead of the table displaying the segment list. This misalignment creates confusion as users may expect the scrollbar to control the table content but find it controls the entire page. | 1.Navigate to the Admin Panel and go to Client Management -> WhatsApp -> Segments. 2.Locate the table displaying the list of segments. 3.Scroll vertically using the scrollbar positioned on the far right side of the page. 4.Observe that the scrollbar controls the page rather than just the table's content. | Bug | Medium | Medium | The vertical scrollbar is misaligned and positioned on the right side of the page. It controls the entire page instead of just the table's content. | The vertical scrollbar should be aligned with the table and should control only the content within the table. It should not control the page's content unless explicitly intended for that purpose. | https://i.postimg.cc/pVKN88TS/segment-can-t-scroll.jpg | To do
15 | WhatsApp->Segments | Inconsistent tense and grammar in success notifications | In the Segments section, after creating a segment, the success notification displays as "Create Successful," and after updating a segment, the notification displays as "Update Successful." These messages are inconsistent with the rest of the site's notifications, which use past tense. The correct messages should be "Created Successfully" and "Updated Successfully," respectively, to maintain grammatical consistency and proper tense usage across the site. | Case 1: Segment Creation 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Segments. 2.Click the Create Segment button and complete the required fields. 3.Click the Submit button to create the segment. 4.Observe the notification message displayed as "Create Successful." Case 2: Segment Update 1.Navigate to the Segments table in Admin Panel -> Client Management -> WhatsApp -> Segments. 2.Toggle the On/Off switch to update a segment's status. 3.Observe the notification message displayed as "Update Successful." | Bug | Low | Low | 1.After creating a segment, the notification reads: "Create Successful." 2.After updating a segment, the notification reads: "Update Successful." | 1.After creating a segment, the notification should read: "Created Successfully." 2.After updating a segment, the notification should read: "Updated Successfully." 3.All success messages across the site should maintain consistent grammar and tense | https://postimg.cc/gallery/LfTtb8M | To do
16 | WhatsApp->Segments | Dropdown icon in table header is non-functional | In the Segments section under Admin Panel -> Client Management -> WhatsApp -> Segments, the table header includes a dropdown icon. However, the icon is non-clickable and does not perform any action, making it redundant and confusing for users. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Segments. 2.Observe the table header in the list of segments. 3.Click on the dropdown icon in the header. 4.Notice that the icon is non-functional and does not trigger any action or dropdown menu. | Bug | Medium | Low | The dropdown icon in the table header is non-functional and does not trigger any action. | 1.The dropdown icon in the table header should be functional. 2.Clicking on the icon should display a dropdown menu with relevant actions or options for the table (e.g., sorting, filtering). 3.If no functionality is intended, the icon should be removed to avoid confusion. | https://i.postimg.cc/8zxdGFSR/why-drpdwn-not-clickable-no-use.jpg | To do | It's not an issue
17 | WhatsApp->Segments | Excessive numeric information in page display of Segments section | In the Segments section under Admin Panel -> Client Management -> WhatsApp -> Segments, a line below the table indicates the number of entries being shown on the page. The current text reads: "Showing 1 to 10 from 12 entries." This format contains excessive numeric information, making it less user-friendly and harder to quickly understand. A better approach would be to simplify the format using page numbers, such as "Page 1 of 2." | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Segments. 2.Scroll to the bottom of the table displaying the list of segments. 3.Observe the text line showing the number of entries displayed on the page (e.g., "Showing 1 to 10 from 12 entries"). | UI/UX Enhancement | Low | Low | The message reads: "Showing 1 to 10 from 12 entries," which includes excessive numeric information. | The message should display simplified information using page numbers, such as: ->"Page 1 of 2." | https://i.postimg.cc/ZYg6pBW1/segment2.jpg | To do | It's not an issue
18 | WhatsApp->Contact List | Incorrect percentage calculation in Contact List segments | In the Admin Panel -> Client Management -> WhatsApp -> Contact List, all contacts are displayed grouped by their respective segments (e.g., HR, SQA, Marketing, Potentials). Each segment shows the percentage of contacts belonging to it. However, the percentages displayed do not sum up to 100%. For instance, one segment might show 30%, another 90%, another 10%, and another 10%, which exceeds 100%. The percentage calculation logic appears to be incorrect. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contact List. 2.Observe the list of contacts grouped by their segments. 3.Check the percentage displayed for each segment. 4.Add contacts across multiple segments to observe the total percentage exceeding 100%. | Bug | High | High | The percentage calculation exceeds 100% across all segments (e.g., one segment shows 30%, another 90%, another 10%, and another 10%). | The total percentage of contacts across all segments should sum up to 100%, distributed correctly based on the number of contacts in each segment. | https://postimg.cc/gallery/8VbxLpL | To do | I think it's ok
19 | WhatsApp->Contact List | Previously entered data auto-fills in the add contact form for a different segment | In the Admin Panel -> Client Management -> WhatsApp -> Contact List section, users can manage contacts categorized by segments such as HR, SQA, Marketing, and Potentials. Each segment has an Add Contact icon to add new contacts under that specific segment. The issue occurs when a user adds contact details for one segment, submits or cancels the operation, and then switches to add contact for a different segment. The form for the new segment automatically pre-fills with data from the previous segment's input. This behavior can lead to errors and confusion for the user. | Navigate to Admin Panel -> Client Management -> WhatsApp -> Contact List. Select a segment (e.g., HR) and click the Add Contact icon. Fill in the contact details (e.g., Name, Phone Number, Email, etc.) and either submit or cancel the operation. Open another segment (e.g., SQA) and click the Add Contact icon. Observe that the input fields are pre-filled with the previous segment's contact details. | Bug | High | Medium | The Add Contact form is pre-filled with data from the last segment where contact details were added. | The Add Contact form should be empty each time it is opened for a new segment. | https://drive.google.com/file/d/1sztENbOYZBJNG5JrlbJcZlOx_4O91VbA/view?usp=drive_link | To do | It's not an issue
20 | WhatsApp->Contact List | Phone number input validation issue in Contact List | In the Admin Panel -> Client Management -> WhatsApp -> Contact List, when adding a contact, the system accepts a phone number with 10 digits. However, the validation message prompts that the phone number should be at least 11 digits. This inconsistency should be addressed, as the system allows input of 10-digit numbers despite the requirement of 11 digits. The system should either enforce the validation or accept a 10-digit phone number, but both actions should align. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contact List. 2.In the contact list, click on the icon to add a new contact. 3.Enter a 10-digit phone number and submit. 4.Observe that the system accepts the 10-digit number and successfully adds the contact. 5.Now, try entering a less than 10-digit phone number and submit. 6.The validation message displays: "Phone number should be at least 11 digits." | Bug | High | High | The system allows a 10-digit phone number to be successfully added, despite the validation message stating the number should be at least 11 digits. | 1.The system should enforce the correct validation rule and not accept any phone number less than 11 digits (if the rule is to accept 11 digits). 2.It should either accept exactly 11 digits or reject less than 11 digits numbers. | https://drive.google.com/file/d/1uhh7EWByuOVZZmt-tZLkl-wQxhyHMSg6/view?usp=drive_link | Ready for QA
21 | WhatsApp->Contact List | Phone number duplication not handled correctly in the Add Contact functionality | In the Admin Panel -> Client Management -> WhatsApp -> Contact List, when a user attempts to add a contact and inputs a phone number that already exists in the list, no error message is shown immediately in the phone number field. The contact is not added, and no notification or indication of the issue is provided to the user. However, when the user opens the Add Contact form again, the error message "Phone number already taken" is displayed, even though no error was shown during the initial attempt. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contact List. 2.Click the icon to add a new contact. 3.Input a phone number that already exists in the contact list. 4.Fill in the remaining fields and click Submit. 5.Observe that the contact is not added, and no error message is shown at the time of submission. 6.Reopen the Add Contact form, and see the error message "Phone number already taken" appear. | Bug | High | High | 1.No error message is shown when a duplicate phone number is entered, and the contact is not added. 2.Only when the user reopens the form does the error message "Phone number already taken" appear, which could confuse the user. | 1.When a user attempts to input a phone number that already exists in the contact list, an immediate error message should appear in the Phone number field, such as: -->"This phone number is already taken." 2.The contact should not be submitted or added until a unique phone number is provided. | https://drive.google.com/file/d/1eDMDfNDl6OsZkakTSBf86036mne6RwFz/view?usp=drive_link | Ready for QA
22 | WhatsApp->Contact List | Add Contact form allows submission without validation for required fields | In the Admin Panel -> Client Management -> WhatsApp -> Contact List, when adding a contact via the Add Contact form, the user can submit the form without entering any required information (e.g., Name, Phone Number, Country, or Segment). No error messages are displayed to indicate the missing data. Although the submission does not result in a new contact being added to the list, the lack of validation and feedback confuses the user. | Navigate to Admin Panel -> Client Management -> WhatsApp -> Contact List. Click the icon to add a new contact. Leave all required fields (e.g., Name, Phone Number, Country, Segment) blank. Click the Submit button. Observe that the form is submitted without error messages, but no contact is added to the list. | Bug | High | High | 1.The form allows submission without any data in the required fields. 2.No error messages are displayed to indicate missing data. 3.No contact is added to the list after submission, but the user is not informed of the issue. | 1.Validation should prevent submission if required fields are left blank. 2.Error messages should be displayed next to each required field, such as: ->"Name is required." ->"Phone number is required." ->"Country is required." ->"Segment is required." 3.The form should not be submitted until all required fields are filled. | https://drive.google.com/file/d/1bjrE6g7hmNQW4hUGnTVDJZi64eVz-QRh/view?usp=drive_link | To do
23 | WhatsApp->Contact List | Dropdown icon in contact list table header is non-functional and displays incorrect tooltip | In the Admin Panel -> Client Management -> WhatsApp -> Contact List, the table header includes a dropdown icon next to the title. However: 1.The dropdown icon is non-functional and does not perform any action when clicked. 2.When the mouse hovers over the dropdown icon, a tooltip appears displaying the text "title", which is both incorrect and irrelevant. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contact List. 2.Observe the table header containing a dropdown icon next to the title. 3.Hover the mouse over the dropdown icon. 4.Click on the dropdown icon. 5.Observe that no action is performed and the tooltip text is incorrect. | Bug | Low | Low | 1.The dropdown icon is non-functional and does not perform any action. 2.The tooltip displays the text "title," which is irrelevant and unclear. | 1.Clicking the dropdown icon should open a menu with relevant actions (e.g., sorting, filtering, etc.) depending on the feature's intended functionality. 2.The tooltip should display meaningful text related to the dropdown's purpose (e.g., "Options," "Sort," "Filter"). | https://drive.google.com/file/d/13U41koMMl-Jkzu0iwWxY9eLBcC3ka6vc/view?usp=drive_link | To do
24 | WhatsApp->Contact List | Pagination buttons in the Segment page highlight multiple buttons simultaneously on hover | In the Admin Panel -> Client Management -> WhatsApp -> Contact List section, the pagination buttons ([Previous, 1, 2, Next]) exhibit incorrect behavior. When hovering over button 2, both buttons 1 and 2 highlight in blue. This behavior is inconsistent and confusing for users, as only the button under the mouse pointer should highlight. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contact List 2.Scroll to the bottom of the page to view the pagination buttons. 3.Hover the mouse over the button labeled 1. ->Observe that it highlights with a blue color (as expected). 4.Hover the mouse over the button labeled 2. ->Observe that both 1 and 2 highlight together, instead of just 2. | Bug | Low | Low | When hovering over button 2, both 1 and 2 highlight with a blue color. | When hovering over any pagination button, only the button directly under the mouse pointer should highlight with a blue color. | https://drive.google.com/file/d/1-wzpH9cNE1m5AFPA4hKv1tmsMxLsrdUB/view?usp=drive_link | To do
25 | WhatsApp->Contact | Image filename exceeds the boundaries of the upload field in "Add New Contact" form | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, when using the Add New button to add a new contact, uploading a contact photo causes the filename of the uploaded image to extend outside the boundaries of the designated photo upload field. This disrupts the UI layout and can confuse the user. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Click on the Add New button to open the form for adding a new contact. 3.In the Upload Photo field, select an image file with a long filename. 4.Observe that the image filename extends outside the designated upload field box. | Bug | Low | Low | The image filename extends beyond the upload field box, affecting the visual design and usability of the form. | The image filename should be truncated or wrapped properly to remain within the boundaries of the upload field box. | https://i.postimg.cc/ZKtbwxzS/contact-photo.jpg | To do
26 | WhatsApp->Contact | Add Contact allows submission of invalid phone numbers not aligned with country format | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, when adding a new contact through the Add New Contact form, the application does not validate phone numbers against the selected country's format. Users can input a phone number that exceeds or is shorter than the required digit length for the selected country and successfully submit the form, resulting in invalid phone numbers being added to the contact list. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Click on the Add New button to open the form for adding a new contact. 3.In the form, select a country (e.g., United States, which supports 10-digit phone numbers). 4.Enter an invalid phone number (e.g., more or fewer than 10 digits for the United States). 5.Submit the form. 6.Observe that the invalid phone number is accepted without any validation errors. | Bug | High | High | 1.The system does not validate the phone number format based on the selected country. 2.Users can submit invalid phone numbers, which are then added to the contact list. | 1.The system should validate the phone number against the selected country's format (e.g., 10 digits for the United States). 2.If the phone number does not meet the required format, an error message should be displayed, and the form submission should be blocked. | https://postimg.cc/gallery/FsGGQpc | Ready for QA
27 | WhatsApp->Contact | Contact List Headers Not Persistent During Scrolling | In the Admin Panel -> Client Management -> WhatsApp -> Contacts page, the contact list is displayed with columns for [name, phone (with country), contact list group name, and segments]. When users scroll down to view more contacts, the column headers are not fixed at the top of the table. This makes it difficult for users to interpret the data as they lose the context of the columns while scrolling. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.View the contact list table with columns for [name, phone (with country), contact list group name, and segments]. 3.Scroll down to view more contacts in the list. 4.Observe that the column headers disappear as the user scrolls down. | Usability Enhancement | Medium | Low | The column headers disappear from view when the user scrolls down, leaving only the contact data visible. | The column headers should remain fixed (persistent) at the top of the table while scrolling, ensuring the user can always see which data corresponds to which column. | https://i.postimg.cc/1tWf2nPQ/contacts-no-head.jpg | To do
28 | WhatsApp->Contact | Non-functional dropdown icon in the contact list table header with irrelevant tooltip | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, the contact list table header includes a dropdown icon. However, this icon is not clickable and does not perform any action. Additionally, when the mouse hovers over the icon, it displays a tooltip with a "#" symbol, which is irrelevant and confusing to the user. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Locate the table displaying the contact list (columns include name, phone with 3.country, contact list group name, and segments). 4.Observe the dropdown icon in the table header. 5.Hover the mouse pointer over the dropdown icon. 6.Attempt to click the dropdown icon. | UI/UX Bug | Low | Low | 1.The dropdown icon is not clickable and does not perform any action. 2.When the mouse hovers over the icon, a small tooltip with the text "#" appears, which is irrelevant and adds confusion. | 1.The dropdown icon should either: ->Perform a meaningful action, such as sorting or filtering the column data, if it is intended to be functional. ->Be removed if it has no purpose in the current design. 2.The tooltip should provide meaningful information or be removed if unnecessary. | https://i.postimg.cc/J48zx5jk/why-here-drpdwn-with-no-use.jpg | To do
29 | WhatsApp->Contact | Misaligned table layout with uneven spacing in the Contacts list page | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, the table displaying the contact list ([Name, Phone with Country, Contact List Group Name, Segments]) is not properly aligned within its container box. There is unnecessary spacing on the left side of the table before it starts, while on the right side, the table ends at the container's edge without any spacing or border, causing the layout to appear unbalanced. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Observe the table containing the contact list within the container box. 3.Check the alignment and spacing of the table on the left and right sides. | UI/UX Bug | Medium | Low | 1.The table starts with unnecessary spacing on the left side. 2.The table ends at the container edge on the right side without spacing or a border. | 1.The table should have consistent spacing on both the left and right sides within the container box. 2.Borders should be properly aligned to create a visually balanced and professional layout. | https://postimg.cc/gallery/zgRYR6S | To do
30 | WhatsApp->Contact | Incorrect and duplicate icons in the Contacts page for SMS and Templates, and wrong View Details icon | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, the contact list is displayed with several icons for actions such as Send SMS, View Details, Send Templates, Edit, Add to Blacklist, and Delete. The issue is as follows: -->The icons for Send SMS and Send Templates are the same, which is confusing. -->The View Details icon is incorrect as it currently represents a Copy Link action instead of viewing the details of the contact. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Look at the icons available for each contact (Send SMS, View Details, Send Templates, Edit, Add to Blacklist, Delete). 3.Observe the following: -->The Send SMS and Send Templates icons are identical. -->The View Details icon is incorrect and looks like a Copy Link icon. | UI/UX Bug | High | Medium | 1.The Send SMS and Send Templates icons are identical. 2.The View Details icon is a Copy Link icon instead of a correct representation for viewing contact details. | 1.The Send SMS and Send Templates icons should be distinct and easily distinguishable. 2.The View Details icon should correctly represent viewing the contact's details (e.g., an eye icon or a details icon), not the Copy Link icon. | https://i.postimg.cc/D0rY7XfS/contact-segments-icon.jpg | To do
31 | WhatsApp->Contact ->Search Box | Search box misalignment when horizontally scrolling in the Contacts page | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, there is a Search box located at the right side corner of the table. The issue occurs when the user horizontally scrolls the table. The Search button does not remain fixed and moves to the left side when scrolling to the right, instead of staying at its original position. This behavior makes it difficult for users to access the search functionality once they scroll horizontally. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Observe the Search box located at the right corner of the table. 3.Scroll horizontally within the table to the right. 4.Notice that the Search button moves to the left as the table is scrolled further. | UI/UX Bug | Medium | Medium | The Search button moves from its fixed position when the user scrolls horizontally, eventually going to the left side of the screen. | 1.The Search button should remain fixed at the right corner of the page, even when the user scrolls horizontally. 2.The button should not move with the horizontal scroll, maintaining its position for easy access. | https://postimg.cc/gallery/0KL0tSd | To do
32 | WhatsApp->Contact | Horizontal scrolling is only available after vertical scrolling in Contacts list page | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, the contact list is displayed in a table within a box. However, the horizontal scroll bar is only visible after the user scrolls vertically, making it difficult to view the entire table's content horizontally. Ideally, the horizontal scroll bar should be accessible at all times without the need to scroll down vertically, allowing users to easily navigate through all table information. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Observe the contact list displayed in the table within the box. 3.Attempt to scroll horizontally without scrolling vertically first. 4.Notice that the horizontal scroll bar is not available initially and only appears after scrolling down vertically. | UI/UX Bug | Medium | Low | The horizontal scroll bar only appears after the user scrolls down vertically, making it harder to view the full table content horizontally. | 1.The horizontal scroll bar should be visible at all times, allowing users to scroll horizontally to view the entire table content without needing to scroll vertically first. 2.The user should be able to scroll both vertically and horizontally independently. | https://i.postimg.cc/XvZrmKxk/conatacts-management.jpg | To do
33 | WhatsApp->Contact | Inconsistent notification message after deleting a contact | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, after deleting a contact, the notification message appears as "deleted". However, for consistency with the rest of the site, the message should be written as "Deleted Successfully" or "Deleted" with proper capitalization and use of the word "Successfully," as is the case for similar actions throughout the platform. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Select a contact and delete it. 3.Observe the notification message that appears after the contact is deleted. | UI/UX Inconsistency | Medium | Low | The notification displays "deleted", which does not match the site's standard format for notifications. | The notification should display "Deleted Successfully" or "Deleted" with proper capitalization to match the site's consistent messaging format. | https://i.postimg.cc/Sx6T88cV/contact-delete.jpg | To do
34 | WhatsApp->Contact->Language | Language change to Bangla not fully applied in Contacts page | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, when the user changes the language to Bangla, several sections and words do not get translated properly, leaving them in English instead of the expected Bangla translation. This issue occurs in multiple parts of the page, making the language feature incomplete and inconsistent. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Change the language from English to Bangla using the language selection option. 3.Observe the page and check the sections and text. 4.Verify if all sections, buttons, and labels are translated to Bangla. | Bug | High | Medium | Some sections and words are not translated to Bangla and remain in English, creating an incomplete language switch. | 1.When switching to Bangla, all relevant sections, labels, buttons, and text should be displayed in the Bangla language. 2.No English text should remain visible when the language is switched. | https://postimg.cc/gallery/RFb5Y6f | To do
35 | WhatsApp->Contact->Import | Overlapping buttons in Bangla language for the Import section in Contacts page | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, when the language is switched to Bangla, in the Import page, the two buttons "আপলোড নিশ্চিত করুন" (Upload Confirm) and "নমুনা ডাউনলোড" (Download Sample) are overlapping. These buttons appear too close together, causing a visual issue and affecting the user interface layout. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Change the language to Bangla using the language selection option. 3.Scroll down to the Import .xlsx file section. 4.Observe the two buttons: "আপলোড নিশ্চিত করুন" and "নমুনা ডাউনলোড". | UI/UX Bug | Medium | Medium | The two buttons "আপলোড নিশ্চিত করুন" and "নমুনা ডাউনলোড" are overlapping, causing a layout issue. 7. Issue Type: | 1.The two buttons should be properly spaced and not overlap when displayed in the Bangla language. 2.Each button should have enough space for clear visibility and ease of use. | https://i.postimg.cc/C1bDzC3s/contact-import-overflow-Btn.jpg | To do
36 | WhatsApp->Contact->Filter | Filter box width misalignment with contact list table in Contacts page | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, the filter box at the top of the page is misaligned in width compared to the contact list table. The filter box appears shorter in width than the contact list box, creating an inconsistent UI layout that affects the user experience. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Click on the Filter option at the top of the page. 3.Observe the filter box that appears above the contact list table. 4.Compare the width of the filter box with the width of the contact list table. | UI/UX Bug | Medium | Low | The filter box is narrower in width compared to the contact list table, causing a visual misalignment. | The filter box width should align perfectly with the width of the contact list table to maintain a consistent UI layout. | https://i.postimg.cc/Z5rCPY7J/contact-filter-con-list-not-alligned.jpg | To do
37 | WhatsApp->Contact ->Import | Incomplete contact import from .xlsx file in Contacts page | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, when importing contacts through a .xlsx file, not all the contacts listed in the file are successfully added to the contact list. For instance, if the uploaded file contains 6 contacts, only 2 are imported and displayed in the contact list, while the remaining contacts are omitted without any error message or notification. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Click on the Import option to upload a .xlsx file. 3.Prepare an .xlsx file with multiple contacts (e.g., 6 contacts) containing the following details: ->Name ->Phone Number ->Segment ->Country ->Contact List Group 4.Upload the file and observe the contacts added to the list. | Bug | High | High | Only 2 out of the 6 contacts in the .xlsx file were successfully added to the contact list. The remaining 4 contacts were omitted without any error message or indication of the problem. | All contacts from the uploaded .xlsx file should be added to the contact list. If any issues occur during the import process, an appropriate error message or notification should be displayed indicating the reason for failure. | https://postimg.cc/gallery/jSrjWrB | To do
38 | WhatsApp->Contact ->Import | Incorrect default country displayed when importing contact list with incomplete data | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, when a user uploads a .xlsx file containing only the name and phone number fields (without specifying the country), the system automatically assigns the country as "United States Minor Outlying Islands." This behavior is incorrect as the system should either: ->Prompt the user to fill in the missing country details. ->Automatically detect the country based on the phone number or leave it blank. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Use the Import option to upload a .xlsx file containing only name and phone number fields. 3.Observe the imported contact details in the contact list. | Bug | High | Medium | The country field is automatically filled with "United States Minor Outlying Islands," even though the user did not specify it in the .xlsx file. | 1.The country field should either remain blank or prompt the user to fill in the missing country information. 2.Alternatively, the system should intelligently detect the country from the phone number (if supported). | https://postimg.cc/gallery/jSrjWrB | To do
39 | WhatsApp->Contact | Inconsistent table format between first and second pages in Contacts list | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, the table format displaying the contact list differs between the first and second pages. -->First Page: Displays columns in the order: List No., Name, Phone, and Contact List. -->Second Page: Displays columns in the order: List No., Name, Phone, Contact List, Segment, and Status. This inconsistency creates confusion for users when navigating through the pages. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Observe the table format on the first page. 3.Navigate to the second page using the pagination controls. 4.Compare the table format on the second page with the first page. | Bug | High | Medium | The first page of the contact list shows fewer columns (List No., Name, Phone, Contact List), while the second page includes additional columns (Segment and Status). | The table format should remain consistent across all pages, displaying the same columns in the same order. | https://postimg.cc/gallery/wJBMvZQ | To do
40 | WhatsApp->Contact->Bulk Action | "Bulk Action" button remains visible even when no contact is selected | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, each row in the contact list includes a selection checkbox. When a contact is selected, a "Bulk Action" button appears at the top of the page. However, the "Bulk Action" button remains visible even after deselecting all contacts. This behavior creates inconsistency as the button should only appear when at least one contact is selected. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Select a contact from the list by clicking the checkbox in its row. 3.Observe that the Bulk Action button appears at the top of the page. Do action in Bulk Action. 4.Now no contact in selection. 5.Observe that the Bulk Action button remains visible even when no contact is selected. | UI/UX Bug | Medium | Medium | The "Bulk Action" button remains visible even after all contacts are deselected, which is inconsistent with expected behavior. | The "Bulk Action" button should: ->Appear only when at least one contact is selected. ->Disappear automatically when all contacts are deselected. | https://drive.google.com/file/d/1KOQSIm4b4KE1dkfP4MJynv_p7YhKVcVj/view?usp=drive_link | To do
41 | WhatsApp->Contact->Bulk Action | No error notification when performing "Bulk Action" without selecting contacts | In the Admin Panel -> Client Management -> WhatsApp -> Contacts section, a "Bulk Action" button appears at the top of the page when a user selects any contact(s) in the contact list. The "Bulk Action" menu provides multiple options like Add List, Remove List, Add Segment, Remove Segment, Add Blacklist, Remove Blacklist, Delete Contacts. However, for the actions Remove List, Add Blacklist, and Remove Blacklist, if the user clicks them without selecting any contact, no error notification or message is displayed to inform the user that no contacts were selected. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts. 2.Without selecting any contact from the list, click on the Bulk Action button. 3.From the dropdown, select any of the following actions: ->Remove List ->Add Blacklist ->Remove Blacklist 4.Observe the behavior after clicking the action. | Bug | High | Medium | No error notification or message appears. The action silently fails without informing the user, creating confusion. | An appropriate error notification should appear, stating: "No contact selected. Please select at least one contact to perform this action." | https://drive.google.com/drive/folders/1m9KddA3IFLFxBK_U_ygnRS5ZjilkCt16?usp=drive_link | Ready for QA
42 | WhatsApp->Contact->Bulk Action | WhatsApp->Contact ->Import | In the Admin Panel -> Client Management -> WhatsApp -> Contacts list page, under the Read By column, the count displayed for a contact is incorrect. For example, it shows "1 Of The 24 Contacts", whereas the total number of available contacts is only 14. This creates confusion and presents misleading data to the user. | 1.Navigate to Admin Panel -> Client Management -> WhatsApp -> Contacts list. 2.Look under the Read By column for any contact. 3.Note the discrepancy between the total contacts mentioned in the Read By count and the actual number of available contacts in the system. | Bug | High | Medium | The Read By column displays an inflated total contact count (e.g., "1 Of The 24 Contacts") that does not match the actual number of contacts available (e.g., 14 contacts). | The Read By count should accurately reflect the number of contacts available in the system. For example, if there are 14 contacts in total, the Read By count should display "1 Of The 14 Contacts" instead of "1 Of The 24 Contacts". | https://drive.google.com/file/d/1akaH0Lm4H6fWfm-mkC49yNJOpA_l5C8f/view?usp=drive_link | Ready for QA | It's not an issue
43 | Unread Text |  | 1. Don't display unread text number from all users. 2. When read unread text, then go back and again text sended from client-end, don't show the unread text number(seen as read text).

## App
Environment : Browser: Chrome 132.0.6834.160 OS: Windows 10 Pro
Tester's Name : Noor Afida Annha |  | Reviewed By :
Date : 02 .02. 2025 |  | Date :
Issue Id | Module | Issue Details | Attachment | Status | Type | Priority | Severity | Comments
1 | Inbox Screen | 1. In inbox screen , when no conversation available ,"No messages yet. Start the conversation!" -> by finger tapping user can move this text. | https://drive.google.com/file/d/1dkhdDYJH33S0YWLyx3zC9v309HXP8XmN/view?usp=drive_link | QA Done | Bug | High | Medium
2 | Inbox Screen-> Clear chat | 1. In inbox screen , when no conversation available,"Clear chat" function shouldn't work. 2. "Are you sure you want to clear chatting history??"--> In this text double question mark shouldn't be , and proper text would be "chat history " not chatting . 3. After one click button should be disable , and instant need to showing notification message. But here user can click more than one click together and also notification message showing correspondly. | https://drive.google.com/file/d/1HgAbJqyyIw9FoonVOxQUIpiXKwfsvnYW/view?usp=drive_link | QA Done | Bug & Improvement | High | Medium
3 | User Profile | 1. When user didn't share any files , in user's profile shouldn't showing "Load More",also in "Media"-> there shoudn't be showing loading something or any exlclamation mark after loading done. (backend issue) 2. In user's profile after tag section , in right corner there is a "yellow-black" box with a text displaying. (done) | https://drive.google.com/file/d/1W4qghO7hx6GjYvSzkg5JElK6xROGRnZ7/view?usp=drive_link | QA Done | Bug | High | Medium | api link : https://api.salebot.app/api/shared-files/19?type=media type(media,file."")
4 | Inbox Screen | 1. When user sending a video only showing a little cross option. Video should be showing like a clip with cross mark. | https://drive.google.com/file/d/1JLgVwiQAqEXOjkxItkdIaVAuKeSesgpp/view?usp=drive_link | QA Done | Bug | High | Medium
5 | Inbox Screen | 1. User shouldn't be able to click on "Unassigned" title . But user can click on this and also a Error notification appearing. | https://drive.google.com/file/d/1QRJYr6e3YN2dpHIK_g885WFKUJH2u2Te/view?usp=drive_link | QA Done | Backend Issue | High | High | rabbi vaia
6 | Contact | 1. Filter-> Seen-> here showing those contact which isn't even start conversation. If no conversation happened then how possible to showing in seen filter?(check in app) 2. In filter two title not showing. (done) | https://drive.google.com/file/d/1fIZstDF-6NIHccEzVMRzukbbNwLK4AXD/view?usp=drive_link | To do | Backend Issue | High | High | filter issue is backend issue. (check in app)
7 | Inbox Screen | 1. After assign a staff not showing the name in UnAssigned Button. | https://postimg.cc/gallery/r8LvqC2 | QA Done | Bug | High | High | delay api call for staff assigned
8 | Inbox Screen | 1. Can't able to assign "Rohim Ahmed". |  | QA Done | Bug | High | High
9 | Coversation | 1. Displaying wrong time. | https://postimg.cc/gallery/TwTKRyq | QA Done | Bug | High | High | show created at time in home screen created_at
10 | Coversation | 1. Displaying seconds in minus(-). | https://i.postimg.cc/Hj1C2znh/reading-Time.jpg | QA Done | Backend Issue | High | High
11 | Chat Icon | 1. In chat icon showing wrong message notification (+9). | https://i.postimg.cc/FKzs1PLy/wrong-message-notification.jpg | QA Done | Backend Issue | Low | High | rabbi vaia "total_unread_messages": 15, "next_page_url": false. | https://api.salebot.app/api/chat-rooms?q=&type=&assignee_id=&tag_id=&is_seen=
12 | Shared files-->Media | 1. In "Media" not load images properly . And showing wrong number (+14 More) 2. "Load More" not clickable. | https://i.postimg.cc/pdfkhZMd/shared-media.jpg | QA Done | Bug | High | Medium | some modification here ui. "Load More" not clickable. initially hide this load more but it needed. | check it
13 | Shared files-->Documents | 1. PDF name not same , also wrong description. | https://i.postimg.cc/KcwpRQ1n/pdf-name-not-same.jpg | To do | Backend Issue | High | High | rabbi vaia check in app end and backend also for pdf name and pdf info. pdf name and pdf send date and time show now. | It's not an issue
14 | Shared files-->Documents | 1. "Hide" functionality get mixed with "Note" . In this way "Hide" function shouldn't work ,not related with it's job. | https://postimg.cc/gallery/F4J8CKJ | QA Done | Bug | High | Medium | Design as like as web[Document click ->send issue--not fixed]
15 | Inbox Screen | 1. Template and headbar colour blend. User experince could be down. | https://i.postimg.cc/DfSJxPBp/template-header-screen-clr-blend.jpg | QA Done | Improvement | Low | Low
16 | Coversation | 1. Re-engagement text showing in conversation but the time not related with the text[need modification] | https://postimg.cc/gallery/9WLwRg4 | To do | Improvement | High | Medium | backend issue(time not properly show, if any message send failed then the last message time show previous delivered message time.
16 | Settings->Profile | 1. Profile picture after upload gets blurry. | https://i.postimg.cc/rmmJnRPG/p-p.jpg | QA Done | Backend Issue | Medium | Medium | image quality stored is very low and give the low quality image from backend side.
17 | Settings->Profile Info | 1. Gmail and phone number has no verfication. So , user can give only single digit in phone number, also non-existing mail[Which even can't create in gmail] [for mail condition work :- one letter/digit+@+one letter/digit+ .com , so following this user can input any mail , {need redirecting link or OTP} ] | https://i.postimg.cc/mr8x1M97/profile.jpg | Not an issue | Backend Issue | High | High | when edit user mail or phone number user verified using otp. (not an issue)
18 | Inbox Screen[click effect] | 1. Every clickable button should to be modify, after one click button should work and also disable , after done first click's work then will work for second click . [Send button, image,video,docs,link,audio etc-- all need to be more user friendly] |  | QA Done | Improvement | Low | High
19 | Login | 1. "Stay logged in" don't work. | https://drive.google.com/file/d/1WtezGICU15ivU0aI7SbSLGuqzTt1QQZh/view?usp=drive_link | QA Done | Bug | High | High | discuss with designer(suggestion autofill) but i need show signed in user list
20 | Login | 1. It should be "Forgot Password" not "Forget Password". | https://i.postimg.cc/N0cxRztH/spelling-forget.jpg | QA Done | Improvement | Low | Low
21 | Settings->Profile | 1. "Log Out" section need to be allign with , there is a space | https://i.postimg.cc/c4WfJ5Rg/log-out-not-allign.jpg | QA Done | Improvement | Low | Low
22 | Inbox Screen | 1. Template not recieved in client-end. [And showed delivery mark, for this circumstance need to display ""Error message"".] (done) 2. After sending template showing notification -> "Created Successfully".(backend issue) |  | QA Done | Bug & Improvement | High | High | First one solved, second one need to improve from backend.
23 | Inbox Screen | 1. For message not delivered displaying three diffrent "error message". | https://postimg.cc/gallery/QDMP6ZP | To do | Backend Issue | High | High | i hope this is not an issue(multiple time multiple error occured. so show multiple errors)--
24 | User Profile | 1. "Tag" color need to change as "Note". |  | QA Done | Improvement | Low | Low
25 | User Profile->Shared Files | 1. No conversation or after "Clear Chat" ->in "Media" displaying "loading failed mark" for backend dummy/previous data. | https://i.postimg.cc/vHBSQDX1/Screenshot-2025-02-09-at-4-16-12-PM.png | QA Done | Backend Issue | High | High
27 | Conversation/Contact -> Tag | 1. Tag not align with time and unassigned. | https://i.postimg.cc/q7tM38r9/tag-not-allign.jpg | QA Done | Improvement | Low | Low
28 | inbox screen | error message not showing in video,image,audio{audio issue new 34 no.}[ showing only on text] |  | QA Done | Bug
29 |  | After reading text still showing unread message number. |  | QA Done | Bug
30 |  | Don't display unread message ,after read one unread text.(most of the time can hold only 1 unread text) |  | QA Done | Backend Issue
31 |  | Template->send button -> after one click need to be disable. |  | QA Done | Bug
32 |  | Unread message don't display each time. |  | QA Done | Backend Issue
33 | inbox screen | audio stay in zero seconds[don't record] and showing a error message from up"Failed to load audio:(0) Source Error". and showing error message "media upload error" | https://postimg.cc/gallery/3THxx7w | To do | Bug
34 | Contact+Conversation | When search a "yellow-black" box appear | https://drive.google.com/file/d/1EVlr_z_w9kJe6tjz4uryC4GmwO9TAv8U/view?usp=drive_link | QA Done | Bug
35 | Conversation | All channel+All Tags+ All agent+ Unseen-Seen -> all of these don't work as search or filtering. when click any of these nothing appear.[ex: from all agent if choose one agent and click on that , nothing appear related with that agent] | https://drive.google.com/file/d/1EVlr_z_w9kJe6tjz4uryC4GmwO9TAv8U/view?usp=drive_link | To do | Bug
36 | Contact | Search bar work but after writting something when user remove that then without pressing "enter" auto refresh and go back to previous state. | https://drive.google.com/file/d/1lRYA61dTszB-JvKpHB35U5YDNvtommmw/view?usp=drive_link | QA Done
37 | User Profile->Shared Files->Link | When user shared a link , in shared files->link -> displaying wrong red code and no ending page. | https://drive.google.com/file/d/11-yLKN8New14OjzhtabnuXBye21QrUqF/view?usp=drive_link | QA Done
38 | Inbox screen | When send a text, image, video anything -> error message not showing after for present text, error message showing when send again. | https://drive.google.com/file/d/1nvqeuVDAtgK3l83auwT2F_2eAEJ0uBL8/view?usp=drive_link | To do | Backend Issue
39 | Contact | 1. Filter not work . |  |  | Backend Issue
40 | Tag | 1. Same tag can't add. 2. Though can't add same tag, deleted a tag from a user and tried to add that tag on another user. But showing already exist.( it will hamper user experince on APP) |  | To do | Bug
41 | Inbox Screen-> AI Reply | 1. In text showing html code.(&#039) | https://i.postimg.cc/j23czxxx/Imported-Photo-1740379873678.jpg | To do | Bug
42 | Client profile->Tags->Add Tag | Add Tag -> Save button need to be disable after one click. |  | QA Done
43 | Filter -> All Tag | New Tag what given to user didn't add in all tag. |  | QA Done
44 | Notification | Notification has no work functionality. |  | To do
45 | Contact+Conversation [Filter] | All agent->here no need to keep client id, (only staff should be here) |  | To do | Backend Issue
46

## SaleBot_Live_Demo
Noor Afida Annha
|  | URL | Attachment | Status | Comments
1 | Landing Page | https://livedemo.salebot.app/ | login_page.JPG | To do
2 | Client Dashboard | https://livedemo.salebot.app/client/dashboard | client-dashboard.JPG | To do
3 | Client Update Profile | https://livedemo.salebot.app/client/profile?2 | client-update-profile.JPG | To do
4 | Client ->My Subscription | https://livedemo.salebot.app/client/my-subscription | client-mySubs.JPG | To do
5 | Client ->My Subscription->Change Plan | https://livedemo.salebot.app/available-plans | client-mySubs-ChangePlan.JPG | To do
6 | Client ->Change Password | https://livedemo.salebot.app/client/password-change | client-password-change.JPG | To do
7 | Login | https://livedemo.salebot.app/login | login__.JPG | To do
8 | SignUp | https://livedemo.salebot.app/register | sign_up.JPG | To do
9 | SignUp->Submit-> Login page | https://livedemo.salebot.app/login | signup_submit.JPG | To do
10 | Forgot Password | https://livedemo.salebot.app/forgot-password | forgot-pass.JPG | To do
11 | Subscription | https://livedemo.salebot.app/admin/subscriptions | admin-subscription.JPG | To do
12 | Ai Writer | https://livedemo.salebot.app/admin/ai-writer | ai_writer.JPG | To do
13 | Payment Method | https://livedemo.salebot.app/admin/payment-gateway | payment_gateway.JPG | To do
14 | Website Settings->All Settings->Ai Chat | https://livedemo.salebot.app/admin/website/ai-chat | website-all-aiChat.JPG | To do
15 | Website Settings->All Settings->CTA | https://livedemo.salebot.app/admin/website/cta | web-all-cta.JPG | To do
16 | Website Settings->Pages | https://livedemo.salebot.app/admin/website/pages/create | web-pages.JPG | To do
17 | Landing Page->Language->Bangla | https://livedemo.salebot.app/bn | landing_bangal.JPG | To do
18 | System Settings->OneSignal | https://livedemo.salebot.app/admin/one-signal-notification | onesignal.JPG | To do
19 | System Settings->Pusher | https://livedemo.salebot.app/admin/pusher-notification | pusher.JPG | To do
20 | System Settings->Language | https://livedemo.salebot.app/admin/languages (when user add a language ) | System-language.JPG | To do
21 | System Settings-> Firebase | https://livedemo.salebot.app/admin/firebase (When user toggle on and submit) | system-firebase.JPG | To do
22 | System Settings-> Country | https://livedemo.salebot.app/admin/countries (whern user delete and edit) | system-country.JPG system-countryy.JPG | To do
23 | Manage Client -> Add client | https://livedemo.salebot.app/admin/clients/create | manage-add-client.JPG | To do
24 | Client profile->Whatsapp->Templates | 1.When click on whatsapp->templates , goes to settings->whatsapp 2.When click on campaigns->whatsApp ->Add new campaigns, goes to settings->whatsapp | whatsapp-template-seeting-whtsapp.mp4 | To do
25 | Client profile->Whatsapp->Chat Widget | https://livedemo.salebot.app/client/chat-widget/list | whtsapp-chat.JPG | To do
26 | Client profile->Whatsapp->Chat Widget | https://livedemo.salebot.app/client/chat-widget/list | chat-addNew.JPG | To do
27 | Client Profile->Telegram->Overview, Groups, Subscribers | https://livedemo.salebot.app/client/telegram/subscribers/list | telegrm-overview.JPG | To do
28 | Client Profile->AI Assistant ->AI Writer | https://livedemo.salebot.app/client/ai-writer | ai-assistant-ai-writer.JPG | To do
29 | Client Profile->AI Assistant ->Setting | https://livedemo.salebot.app/client/ai-writer-setting | ai-assistant-setting.JPG | To do
30 | Client Profile->Setting ->General Setting | https://livedemo.salebot.app/client/general-settings | setting-general.JPG | To do
31 | Client Profile->Setting ->Billing Details | https://livedemo.salebot.app/client/billing/details | setting-billing-details.JPG | To do
32 | 1.Client Profile->Setting ->Telegram, Whatsapp 2. API (same issue) | https://livedemo.salebot.app/client/whatsapp-settings | setting-whatsapp.JPG | To do
33 | 1.Client Profile->Team Member, My ticket | https://livedemo.salebot.app/client/team/create | team-member.JPG | To do
34 | Client Profile->Inbox | https://livedemo.salebot.app/client/chat | inbox.JPG | To do
35 | Client Profile->Campaigns->WhatsApp | https://livedemo.salebot.app/client/whatsapp/campaigns?campaign_type=whatsapp | campaigns-whatsapp.JPG | To do
36 | Client Profile->Campaigns->Telegram | https://livedemo.salebot.app/client/telegram/campaigns?campaign_type=telegram | campaigns-telegram.JPG | To do
37 | Manage Client->SMS Marketing->Broadcast | https://livedemo.salebot.app/client/sms/campaign/create | sms-broadcast.JPG | To do
38 | Manage Client->SMS Marketing-> Template | https://livedemo.salebot.app/client/sms/template | sms-template.JPG | To do
39 | Manage Client->SMS Marketing-> Provider | https://livedemo.salebot.app/client/sms/provider | sms-provider.JPG | To do
40 | Manage Client->SMS Marketing-> History log | https://livedemo.salebot.app/client/sms/history/list | sms-history.JPG | To do
41 | Subscription(js file) --> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740656662 | subs_js | To do | all of the js file has same issues( 2 .submit(), 1 .click() ,& 5 .focus() ) . Here .focus() calculated because in envato file they didn't give all the functions name which shouldn't use . so from chatgpt found out more functions which shouldn't use and .focus() is one of them .
42 | Price Plan(js file) --> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740658897 | price-plan | To do
43 | Manage Client(js)--> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740886143 | manage_client | To do
44 | All Staff(js)--> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740888420 | All_Staff | To do
45 | All Staff[Add Staff] (js)--> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740889152 | allStaff_addStaff | To do
46 | StaffRole (js)--> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740889802 | StaffRole | To do
47 | StaffRole[Add Role] (js)--> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740890410 | addRole | To do
48 | Ai Assistant[Ai Writter] (js)--> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740890922 | aiWritter | To do
49 | Payment Gateway (js)--> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740892555 | payment | To do
50 | Support[Ticket] (js)--> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740894583 | Support-Ticket | To do
51 | Support [Department] (js)--> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740901473 | Support-Department | To do
52 | Website Settings [Pages] (js)--> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740906136 | Website->pages | To do
53 | Website Settings [All Settings -> Theme] (js)--> find 2 (.submit()) , 1 (.click()) & 5 (.focus()) | https://livedemo.salebot.app/public/admin/js/app.js?v=1740907146 | Web-all-theme | To do
54 | Price Plan(Demo+Local), Subscription | two notification appears for one creation. | add_subs_.JPG | To do
55 | Price Plan(Demo) | https://livedemo.salebot.app/admin/plans/create | price_plan.JPG price-plans.JPG | To do
56 | Subscription( Local+Demo) | User can input minus value in place of amount | sus.JPG | To do
57 | Subscription( Demo) | https://livedemo.salebot.app/admin/subscriptions | subs_active-.JPG | To do
58 | Subscription [Add Extra Credit] ( Local+Demo) | user can input minus value in place of every Limit field. | subs_add_extra.JPG | To do
59 | Staff [All Staff-Add Staff ] | https://livedemo.salebot.app/admin/staffs/create | all-staff-console.JPG | To do
60 | Staff [ Roles ] | https://livedemo.salebot.app/admin/roles | roles-delete.JPG | To do
61 | Support[Department] | https://livedemo.salebot.app/admin/departments | support-dept.JPG | To do
62 | Addon [ Uploads ] | https://livedemo.salebot.app/admin/addon | addon-upload.JPG | To do
63 | Notification | https://livedemo.salebot.app/admin/custom-notification/create | notification-action.JPG | To do
59 |  |  |  | To do
59 |  |  |  | To do
59 |  |  |  | To do
59 |  |  |  | To do

## Latest Version SaleBot
Environment : Browser: Chrome 132.0.6834.160 OS: Windows 10 Pro
Tester's Name : Noor Afida Annha |  | Reviewed By :
Date : 02 .02. 2025 |  | Date :
Issue Id | Module | Issue Details | Attachment | Status | Comments
1 | Website Settings -> All Settings -> Partner Logo | https://stag.salebot.app/admin/website/partner-logo | PARTNER_LOGO.JPG | To do
2 | Website Settings -> All Settings ->FAQ | https://stag.salebot.app/admin/website/faqs | faq.JPG | To do
3 | Website Settings -> All Settings ->Feature | https://stag.salebot.app/admin/website/feature | feature.JPG | To do
4 | Website Settings -> All Settings -> Unique Feature | https://stag.salebot.app/admin/website/unique-feature | UNique_feature.JPG | To do
5 | Website Settings -> All Settings -> Testimonials | https://stag.salebot.app/admin/website/testimonials | testimonials.JPG | To do
6 | Website Settings -> All Settings -> Use Case | https://stag.salebot.app/admin/website/use-case | Use_Case.JPG | To do
7 | Website Settings -> All Settings -> Nav More | https://stag.salebot.app/admin/website/nav-more | Nav_More.JPG | To do
8 | Website Settings -> All Settings -> Google SetUp | https://stag.salebot.app/admin/google-setup | google_setUp.JPG | To do
9 | Website Settings -> All Settings -> Facebook Pixels | https://stag.salebot.app/admin/facebook-pixel | fb_pixel.JPG | To do
10 | Website Settings -> All Settings -> Partner Logo | Search option not work. | partner_logo_search.mp4 | To do
11 | Website Settings -> All Settings -> Story | Search option not work. |  | To do
12 | Website Settings -> All Settings -> Unique Feature | Search option not work. |  | To do
13 | Website Settings -> All Settings ->Feature | Search option not work. |  | To do
14 | Website Settings -> All Settings -> Testimonials | Search option not work. |  | To do
15 | Website Settings -> All Settings -> Advantage | Search option not work. |  | To do
16 | Website Settings -> All Settings -> CTA | 1. Disable function don't work. 2. In page showing " Chat Us" button but in CTA only one action button field available. | bandicam 2025-03-17 15-29-06-830.mp4 | To do
17 | Website Settings -> All Settings -> Use Case | Search option works only on description not on title. |  | To do
18 | Website Settings -> All Settings -> Nav More | Search option works only on description not on title. |  | To do
19 | Website Settings -> All Settings -> Website SEO and OG | Meta keywords -> after writting a keyword when press enter page auto reload and gone previous data. | website seo.mp4 | To do
20 | Website Settings -> All Settings -> Testimonials, Ai Chat, Section Title Subtitle(Unique Feature Section Title) , Hero section(Description), | not available in the [salemag] theme. |  | To do
21 | Website Settings -> All Settings ->Story, Advantage | Can add empty story and advantage( though no required field available. ) | advantage-add.JPG story-add.JPG |  | Is it feature? Maybe Modify would be better ( if add required function for any field, then it will not be empty.)
22 | Landing Page | Login option not available in mobile view ( SaleMag theme. )
18
19
20
21
23
24
25
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46